## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Product Release | Marah H | 2022-09-02 | 2022-10-10 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| إدارة الغرف |  | Marah H |  | 2022-09-03 | 2022-09-13 | 10 | Complete
| تصميم واجهات الإضافة و الحذف و التعديل |  | Hiba Ag |  | 2022-09-03 | 2022-09-07 | 4 | Complete
| كتابة الاجرائيات و التوابع المناسبة على قاعدة البيانات |  | Fatya Ab |  | 2022-09-07 | 2022-09-12 | 5 | Complete
| تحقيق الكود البرمجي |  | Marah H |  | 2022-09-09 | 2022-09-13 | 4 | Overdue
| إصدار فواتير الزائن |  | Fatya Ab |  | 2022-09-16 | 2022-09-24 | 8 | In Progress
| تصميم واجهة اصدار الفاتورة |  | Marah H |  | 2022-09-16 | 2022-09-17 | 1 | In Progress
| تصميم شكل الفاتورة الورقية الناتجة |  | Hiba Ag |  | 2022-09-17 | 2022-09-21 | 4 | Not Started
| كتابة الكود المناسب و التحقق من الطباعة |  | Fatya Ab |  | 2022-09-22 | 2022-09-24 | 2 | Not Started
| النسخ الاحتياطي |  | Hiba Ag |  | 2022-09-25 | 2022-10-05 | 10 | Not Started
| كتابة اكواد النسخ |  | Marah H |  | 2022-09-25 | 2022-09-29 | 4 | Not Started
| تحديد مكان النسخ الاحتياطي |  | Hiba Ag |  | 2022-09-24 | 2022-10-02 | 8 | Not Started
| اختبار عملية النسخ و الاسترجاع |  | Fatya Ab |  | 2022-10-02 | 2022-10-05 | 3 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.